## Sheet1
Item	Status	Priority	System	Notes	Cost		Total Expected Cost
Vinyl wrap black	Finished	1	Chassis	COMPLETE	50		3185
Fabricate Battery Cradle	In Progress	1	Chassis	Not Started, price???	200
Mount Radiator, Fan, and Pump	In Progress	1	Chassis	This is a fun project that could be completed soon!!!	10
Machine Aluminum Motor Pate	In Progress	1	Chassis	Not Started	200
Ignition Wiring	Finished	1	Electrical	COMPLETE	0
Left Control Wiring	Finished	1	Electrical	COMPLETE	0
Build Battery	In Progress	1	Electrical	Start with mockups using mostly empty cell banks	100
Get Chain/Sprocket	On Hold	2	Chassis	530 chain, mcmaster 11t front and JT 46t rear	180
Get Motor	On Hold	2	Chassis	ME1616 Water Cooled	1000
Headlight/taillight	In Progress	2	Electrical	Make sure Taillight brakes work	0
Horn power wiring	In Progress	2	Electrical	just connect to power pin.	0
Get Motor Controller	On Hold	2	Electrical	Sevcon? Or what	700
Get ElCon Charger from AliExpress	In Progress	2	Electrical		500
Rebuild Fork	On Hold	3	Chassis	Take to super plush	245
3D Print a cool gas cap	On Hold	3	Chassis		0
Turn Signals	In Progress	3	Electrical	Front need replaced or superglued together.	0
j1772 wiring	In Progress	3	Electrical	wires from connector to Body Controller	0
Clean Wheels	In Progress	5	Chassis	Not complete. Try using simple green	0
Clean Rear Swing Arm	In Progress	5	Chassis	Not complete. Try using simple green	0